## Backlog
Story ID | Epic | User Story | Acceptance Criteria | Priority | Story Points | Sprint | Owner | Status
US-01 | KPI Framework | Standardize KPIs across departments | CFO approves KPI glossary | Must | 5 | Sprint 1 | Business Analyst | Done
US-02 | Data Integration | Consolidate finance data into single dataset | Dataset reconciles with ERP totals | Must | 8 | Sprint 1 | Data Analyst | Done
US-03 | Executive Dashboard | Create executive financial health dashboard | KPI tiles visible and refresh correctly | Must | 5 | Sprint 2 | BI Developer | Done
US-04 | Variance Analysis | Display revenue variance and variance % | Variance measures reconcile with dataset | Must | 5 | Sprint 2 | FP&A Analyst | Done
US-05 | Department Drilldown | Enable department drilldowns | Filters show accurate totals | Should | 3 | Sprint 3 | BI Developer | Done
US-06 | Scenario Modeling | Allow leadership scenario planning | Excel model built for scenarios | Should | 8 | Sprint 3 | FP&A Analyst | Done
US-07 | SQL Validation | Validate KPIs with SQL queries | Totals match dataset | Must | 5 | Sprint 2 | Data Analyst | Done
US-08 | Governance Docs | Create BRD and data dictionary | Docs approved by stakeholders | Must | 3 | Sprint 1 | Business Analyst | Done
US-09 | Executive Reviews | Monthly dashboard review | Leadership uses dashboard | Should | 3 | Sprint 4 | Business Analyst | Planned
US-10 | Forecasting | Predict future revenue trends | Forecast model available | Could | 8 | Sprint 4 | FP&A Analyst | Planned

## Sprint_Planning
Sprint | Planned Story Points | Completed Story Points
Sprint 1 | 13 | 13
Sprint 2 | 15 | 15
Sprint 3 | 11 | 11
Sprint 4 | 11 | 0

## Epic_Progress
Epic | Total Stories | Completed Stories
KPI Framework | 1 | 1
Data Integration | 1 | 1
Executive Dashboard | 1 | 1
Variance Analysis | 1 | 1
Department Drilldown | 1 | 1
Scenario Modeling | 1 | 1
Governance | 1 | 1
Forecasting | 1 | 0