## User_Story_Backlog
Story ID | Epic | User Story | Business Value | Acceptance Criteria | Priority | Story Points | Sprint | Status | Owner | Created Date | Notes
US-001 | Executive Dashboard | As an executive sponsor, I want to see total revenue KPIs so I can quickly understand marketplace performance | Enable faster executive decision making | KPI totals reconcile with dataset and SQL queries | High | 5 | Sprint 1 | Completed | Jamie Christian | 2026-03-01 | Core KPI implementation
US-002 | Revenue Analytics | As a finance analyst, I want profit and revenue metrics so financial performance can be monitored | Improve financial visibility | Revenue and profit margin calculations match dataset | High | 5 | Sprint 1 | Completed | Jamie Christian | 2026-03-01 | Financial metrics validation
US-003 | Conversion Funnel | As a product manager, I want to visualize the customer funnel so I can identify drop‑off stages | Improve checkout conversion optimization | Funnel values match dataset counts and percentages | High | 8 | Sprint 1 | Completed | Jamie Christian | 2026-03-02 | Funnel visualization implemented
US-004 | Category Insights | As a marketing manager, I want to analyze revenue by category so I can optimize campaigns | Support marketing optimization decisions | Category totals reconcile with dataset | Medium | 5 | Sprint 2 | Completed | Jamie Christian | 2026-03-03 | Category analysis built
US-005 | Device Segmentation | As a product analyst, I want device performance insights so we can optimize mobile experience | Improve mobile conversion strategy | Device revenue totals match dataset values | Medium | 3 | Sprint 2 | Completed | Jamie Christian | 2026-03-03 | Device segmentation dashboard
US-006 | Date Filtering | As a user, I want to filter analytics by time period so I can analyze trends | Enable trend analysis and reporting | Date filter updates all visuals correctly | Medium | 3 | Sprint 2 | Completed | Jamie Christian | 2026-03-04 | Date slicer functionality
US-007 | Category Drilldown | As a business analyst, I want drill‑down capability so stakeholders can explore deeper product insights | Improve exploratory analysis | Drill‑down from category to product works correctly | Medium | 5 | Sprint 3 | Completed | Jamie Christian | 2026-03-05 | Interactive drilldown
US-008 | Executive Summary Page | As leadership, we want a high‑level dashboard page so performance can be reviewed quickly | Improve executive reporting efficiency | KPI summary page loads correctly and matches dataset totals | High | 5 | Sprint 3 | Completed | Jamie Christian | 2026-03-06 | Executive dashboard page
US-009 | Refresh Validation | As a business analyst, I want refresh validation so data accuracy is maintained | Improve trust in analytics | Dashboard refresh reflects latest dataset values | Medium | 3 | Sprint 3 | Completed | Jamie Christian | 2026-03-07 | Refresh pipeline validated
US-010 | Export Reporting | As a stakeholder, I want to export reports so insights can be shared with leadership | Enable stakeholder reporting and presentations | Exported report matches dashboard values | Low | 2 | Sprint 3 | Completed | Jamie Christian | 2026-03-08 | Export functionality validated

## Epics
Epic ID | Epic Name | Description | Business Outcome | Owner
EP-01 | Executive Dashboard | Provide leadership with KPI overview | Enable faster strategic decisions | Jamie Christian
EP-02 | Revenue Analytics | Track revenue, profit, and margin | Improve financial transparency | Jamie Christian
EP-03 | Customer Funnel | Analyze customer journey stages | Identify conversion optimization opportunities | Jamie Christian
EP-04 | Marketing Insights | Provide category and segmentation insights | Support marketing performance optimization | Jamie Christian

## Sprint_Backlog
Sprint | Story ID | Task | Owner | Status | Completion Date
Sprint 1 | US-001 | Create revenue KPI tiles | Jamie Christian | Completed | 2026-03-02
Sprint 1 | US-002 | Implement profit margin calculation | Jamie Christian | Completed | 2026-03-02
Sprint 1 | US-003 | Build funnel visualization | Jamie Christian | Completed | 2026-03-03
Sprint 2 | US-004 | Create category revenue chart | Jamie Christian | Completed | 2026-03-04
Sprint 2 | US-005 | Implement device segmentation visuals | Jamie Christian | Completed | 2026-03-04
Sprint 2 | US-006 | Add date slicer functionality | Jamie Christian | Completed | 2026-03-05
Sprint 3 | US-007 | Enable category drill‑down interaction | Jamie Christian | Completed | 2026-03-06
Sprint 3 | US-008 | Design executive summary dashboard | Jamie Christian | Completed | 2026-03-07
Sprint 3 | US-009 | Validate dashboard refresh pipeline | Jamie Christian | Completed | 2026-03-08
Sprint 3 | US-010 | Implement export reporting feature | Jamie Christian | Completed | 2026-03-09