## User Story Backlog
Story ID | Epic | Sprint | User Story | Business Value | Acceptance Criteria | Priority | Story Points | Status | Notes
US-01 | Executive Dashboard | Sprint 1 | As an executive sponsor, I want to view GMV and Orders so I can monitor marketplace performance | Faster leadership decision-making and performance monitoring | GMV and Orders KPI tiles match dataset totals | High | 5 | Ready | Supports executive KPI monitoring
US-02 | Revenue Analytics | Sprint 1 | As a finance analyst, I want marketplace revenue metrics so financial performance can be validated | Ensures financial accuracy and reporting transparency | Revenue KPI reconciles with dataset and SQL validation | High | 5 | Ready | Critical financial validation
US-03 | Take Rate Validation | Sprint 1 | As a finance analyst, I want take rate calculations so revenue percentage can be validated | Improves profitability analysis and pricing insight | Take Rate % equals Revenue divided by GMV | High | 3 | Ready | Important financial KPI
US-04 | Category Insights | Sprint 2 | As a marketing manager, I want category performance insights so I can optimize marketing campaigns | Helps identify high-performing product categories | Category charts match dataset totals and rankings | Medium | 3 | Ready | Supports marketing optimization
US-05 | Seller Performance | Sprint 2 | As a marketing manager, I want seller-level insights so I can identify top-performing sellers | Improves seller performance monitoring and partnership decisions | Seller visual matches dataset aggregation | Medium | 3 | Ready | Supports seller strategy
US-06 | Filtering Capability | Sprint 2 | As a user, I want category and date filters so I can analyze trends more effectively | Allows flexible data exploration and trend analysis | Filters update all visuals correctly | Medium | 2 | Ready | Improves usability
US-07 | Export Reporting | Sprint 3 | As a business analyst, I want to export dashboard insights so stakeholders can review reports | Improves communication and reporting efficiency | Exported data matches dashboard values | Low | 2 | Ready | Supports stakeholder reporting
US-08 | Executive Decision Support | Sprint 3 | As an executive sponsor, I want a clear dashboard summary so I can make fast business decisions | Provides leadership with quick actionable insights | Dashboard provides clear KPI overview | High | 5 | Ready | Executive decision support

## Epics
Epic ID | Epic Name | Description | Business Value | Owner
EP-01 | Executive Dashboard | Provide leadership visibility into marketplace KPIs | High business visibility into revenue and orders | Executive Sponsor
EP-02 | Revenue Analytics | Validate financial performance metrics | Ensures accurate financial reporting | Finance Analyst
EP-03 | Category Insights | Provide category-level performance insights | Improves marketing and product strategy | Marketing Manager
EP-04 | Reporting & Export | Allow export and sharing of analytics insights | Improves reporting and stakeholder communication | Business Analyst

## Sprint Backlog
Sprint | Story ID | Task | Owner | Status
Sprint 1 | US-01 | Build GMV KPI tile | Developer | Completed
Sprint 1 | US-02 | Build revenue KPI | Developer | Completed
Sprint 1 | US-03 | Implement take rate calculation | Developer | Completed
Sprint 2 | US-04 | Create category performance chart | Developer | Completed
Sprint 2 | US-05 | Create seller performance visual | Developer | Completed
Sprint 2 | US-06 | Implement dashboard filters | Developer | Completed
Sprint 3 | US-07 | Add export reporting feature | Developer | Completed
Sprint 3 | US-08 | Finalize executive dashboard layout | Developer | Completed