## Cover
FPnA_Executive_Analytics_Project
Dashboard Alignment
KPI/field naming in this workbook matches the uploaded dashboard file.

## Stakeholders
Name | Role | Team | Influence | Interest | Decision Rights
Angela Morrison | CFO | Finance | High | High | Approve KPI defs
Simone Alvarez | FP&A Manager | Finance | Med | High | Variance narrative signoff
Priya Nair | RevOps Manager | RevOps | Med | High | Data quality signoff

## RAID
ID | Type | Description | Owner | Probability | Impact | Mitigation | Status
R-01 | Risk | Definition drift across teams | BA | Med | High | Lock KPI glossary + signoff | Open
I-01 | Issue | Late data refresh breaks month totals | Data Eng | Low | Med | Add refresh checks + alerts | In Progress

## MoSCoW
ID | Requirement | Must | Should | Could | Won't | Notes
REQ-01 | KPI tiles + filters | Y |  |  |  | Matches dashboard measures
REQ-02 | Drilldowns by key dimensions |  | Y |  |  | Category/Device/Dept/Zone as applicable
REQ-03 | Scenario sheet |  |  | Y |  | What-if modeling in Excel

## Traceability
Req ID | Requirement | User Story | Acceptance Criteria | Dashboard Element | Data Fields | SQL Ref | Test Case
REQ-01 | KPI tiles aligned | US-01 | Totals reconcile | Dashboard KPI tiles | DataTbl | Q1 | TC-01
REQ-02 | Drilldown views | US-02 | Filters consistent | Breakdown charts | DataTbl | Q2 | TC-02

## Data
MonthYear | Department | Revenue Actual | Revenue Budget | Revenue Variance | Revenue Variance % | Opex (Positive) | Operating Income | Gross Margin %
2025-07 | Customer Success | 368128 | 368058 | 70 | 0.0002 | 179957 | -10631 | 0.46
2025-07 | G&A | 375318 | 379194 | -3876 | -0.0102 | 202589 | 33448 | 0.6289
2025-07 | Marketing | 360350 | 357162 | 3188 | 0.0089 | 199089 | -33529 | 0.4594
2025-07 | Product | 545938 | 535758 | 10180 | 0.019 | 187349 | 172056 | 0.6583
2025-07 | Sales | 547941 | 547629 | 312 | 0.0006 | 229277 | 152440 | 0.6966
2025-08 | Customer Success | 453624 | 459148 | -5524 | -0.012 | 256352 | 47787 | 0.6705
2025-08 | G&A | 315498 | 313903 | 1595 | 0.0051 | 223975 | -72819 | 0.4791
2025-08 | Marketing | 563998 | 560871 | 3127 | 0.0056 | 250809 | 205761 | 0.8095
2025-08 | Product | 367367 | 366290 | 1077 | 0.0029 | 167501 | 93303 | 0.7099
2025-08 | Sales | 421203 | 420810 | 393 | 0.0009 | 280579 | 4024 | 0.6757
2025-09 | Customer Success | 403447 | 409625 | -6178 | -0.0151 | 184163 | 22662 | 0.5126
2025-09 | G&A | 409922 | 400951 | 8971 | 0.0224 | 230144 | 18316 | 0.6061
2025-09 | Marketing | 539321 | 532186 | 7135 | 0.0134 | 228081 | 130411 | 0.6647
2025-09 | Product | 442166 | 432224 | 9942 | 0.023 | 193645 | 80992 | 0.6211
2025-09 | Sales | 379354 | 380390 | -1036 | -0.0027 | 192579 | -45379 | 0.388
2025-10 | Customer Success | 396335 | 398125 | -1790 | -0.0045 | 215704 | -35642 | 0.4543
2025-10 | G&A | 398136 | 399636 | -1500 | -0.0038 | 211893 | -29583 | 0.4579
2025-10 | Marketing | 405994 | 394493 | 11501 | 0.0292 | 251929 | -24565 | 0.56
2025-10 | Product | 353517 | 354964 | -1447 | -0.0041 | 233836 | -36947 | 0.5569
2025-10 | Sales | 422336 | 429142 | -6806 | -0.0159 | 245744 | -17481 | 0.5405
2025-11 | Customer Success | 493846 | 501708 | -7862 | -0.0157 | 163255 | 113814 | 0.561
2025-11 | G&A | 568661 | 568852 | -191 | -0.0003 | 182465 | 165940 | 0.6127
2025-11 | Marketing | 498862 | 507720 | -8858 | -0.0174 | 269842 | 71519 | 0.6843
2025-11 | Product | 485077 | 480689 | 4388 | 0.0091 | 197041 | 121126 | 0.6559
2025-11 | Sales | 477874 | 480001 | -2127 | -0.0044 | 172471 | 172902 | 0.7227
2025-12 | Customer Success | 365398 | 364104 | 1294 | 0.0036 | 289688 | -163354 | 0.3457
2025-12 | G&A | 481112 | 493028 | -11916 | -0.0242 | 185946 | 82885 | 0.5588
2025-12 | Marketing | 361316 | 369756 | -8440 | -0.0228 | 199083 | -5973 | 0.5345
2025-12 | Product | 618126 | 618687 | -561 | -0.0009 | 247786 | 155034 | 0.6517
2025-12 | Sales | 508436 | 505265 | 3171 | 0.0063 | 208170 | 79431 | 0.5657

## KPI_Calc
KPI Calculations (Dashboard-aligned)
Metric | Value
Revenue Actual | 13328601
Revenue Budget | 13330369
Revenue Variance | -1768
Revenue Variance % | -0.00013263
Opex (Positive) | 6480942
Operating Income | 1447948
Gross Margin % | 0.58343

## Pivot_Summary
Pivot-style Summaries (Dashboard terms)
MonthYear | Revenue Actual | Revenue Budget | Operating Income
2025-07 | 2197675 | 2187801 | 313784
2025-08 | 2121690 | 2121022 | 278056
2025-09 | 2174210 | 2155376 | 207002
2025-10 | 1976318 | 1976360 | -144218
2025-11 | 2524320 | 2538970 | 645301
2025-12 | 2334388 | 2350840 | 148023

## Charts
Charts

## Scenario
Scenario Modeling (What-if)
Inputs are editable. KPIs are linked from KPI_Calc. Use this for advanced BA-style analysis.
Input | Value | Description
Revenue Actual Lift % | 0.03 | Expected uplift vs baseline
Opex (Positive) Reduction % | 0.04 | Expected OpEx reduction
Gross Margin % Lift (pp) | 0.5 | Margin improvement
Outputs
Metric | Formula
Modeled Operating Income Change | -215799.24