## Defect_Log
UAT Defect Log
Track defects discovered during user acceptance testing. Complete blue cells, update workflow status through closure, and capture evidence or retest notes as needed.
Defect ID | Test Case ID | Module / Feature | Scenario | Defect Summary | Severity | Priority | Status | Assigned To | Reported By | Date Found | Expected Result | Actual Result | Reproducible (Y/N) | Target Fix Date | Retest Date | Notes
DEF-001 | TC-LOGIN-01 | Authentication | Valid login with active user | Login button does not respond on first click | High | High | Open | Dev Team | Jamie Christian | 2026-03-10 | User is logged in successfully | No action occurs until second click | Y | 2026-03-12 |  | Affects first-time login
DEF-002 | TC-DASH-04 | Dashboard Filters | Filter by department | Department filter excludes one valid department from results | Medium | Medium | In Retest | BI Team | Jamie Christian | 2026-03-10 | All departments appear in filter | One valid department is missing | Y | 2026-03-13 |  | Needs data model review
DEF-003 | TC-EXP-02 | Export | Export report to Excel | Exported file drops conditional formatting on variance column | Low | Low | Closed | BI Team | Jamie Christian | 2026-03-10 | Formatting is preserved in export | Formatting removed in exported file | Y | 2026-03-11 | 2026-03-12 | Closed after patch
Note on F3: Severity scale: Critical = showstopper / no sign-off; High = major business impact; Medium = workaround exists; Low = minor issue.
Note on H3: Suggested workflow: Open → In Progress → Ready for Retest → In Retest → Closed. Use Deferred or Blocked where appropriate.

## UAT_Summary
UAT Summary
Project Name | FP&A Executive Analytics Project | Instructions
System / Application | Executive Dashboard | 1. Update project details in blue cells.
UAT Start Date | 2026-03-10 | 2. Log every UAT issue on the Defect_Log sheet.
UAT End Date |  | 3. Review severity and status counts daily.
Prepared By | Jamie Christian | 4. Use the recommendation as an input to formal sign-off.
Version | 1.0
Defect Status Summary |  | Severity Exposure
Total Defects Logged | 3 | Critical Open | 0
Open | 1 | High Open | 1
In Progress | 0 | Medium Open | 1
Ready for Retest | 0 | Low Open | 0
In Retest | 1
Closed | 1
Deferred | 0
Blocked | 0
Release Readiness |  | Daily Status Notes
Critical defects cleared? | Yes | Document daily status, sign-off conditions, workarounds, and final business decision notes here.
High defects acceptable? | Yes
All blocking defects resolved? | Yes
Overall recommendation | Recommended for Sign-Off

## Sign_Off
UAT Sign-Off
Project Name | FP&A Executive Analytics Project |  | Current Recommendation
Release / Version | 1.0 |  | Recommended for Sign-Off
Business Owner |  |  | Open Critical / High | 0 / 1
UAT Lead | Jamie Christian |  | Sign-Off Date
Sign-Off Decision Matrix
Role | Name | Title | Decision | Date | Comments
Business Owner |  |  | Pending
UAT Lead | Jamie Christian |  | Pending
Project Sponsor |  |  | Pending
Technology Owner |  |  | Pending
Final Approval Notes
Summarize residual risk, production readiness, agreed workarounds, and any post-release actions.